RCPSP Solver

Code Documentation & Explanation

Tabu Search & Simulated Annealing for the Resource-Constrained Project Scheduling Problem

# Table of Contents

# 1. Overview

This program solves the Resource-Constrained Project Scheduling Problem (RCPSP) using two metaheuristic algorithms: Tabu Search (TS) and Simulated Annealing (SA). The user can choose to run either algorithm or both in sequence, with a user-specified computation time limit.

## 1.1  What is the RCPSP?

The RCPSP is a classic combinatorial optimisation problem. You have a set of activities (tasks) that must be scheduled. Two types of constraints must be respected:

- Precedence constraints: certain activities cannot start until other activities have finished. These are represented as a directed acyclic graph (DAG) where an arrow from activity A to activity B means B cannot start before A finishes.

- Resource constraints: at every moment in time, the total usage of each renewable resource across all currently-running activities cannot exceed the available amount of that resource.

The objective is to minimise the makespan — the total time from the start of the project to the finish of the last activity.

Example: imagine scheduling construction tasks for a building. You cannot lay the roof before the walls are built (precedence). And you only have 8 workers available at a time (resource). The RCPSP finds the fastest schedule that respects both.

## 1.2  What the Program Does

- Reads a project instance from a .rcp file (activities, durations, resource requirements, precedence structure).

- Asks the user for a computation time limit and a method choice (TS, SA, or A for both).

- Runs the chosen algorithm(s) until time runs out.

- Outputs the best activity sequence found and its makespan.

# 2. Code Structure

The file contains 10 functions defined in a logical top-down order. Each function has a single clear responsibility. The chart below shows the calling hierarchy.

| Function | Role |
| --- | --- |
| main() | Entry point. Reads input, asks user for settings, dispatches to TS or SA. |
| input() | Reads the .rcp file and loads all project data into global arrays. |
| buildReachability() | Precomputes which activities are (indirect) successors of each other. |
| computeLST() | Critical Path Method: computes the Latest Start Time for every activity ignoring resources. |
| generateInitialSolution() | Builds a smart starting sequence ordered by LST (most time-critical activities first). |
| generateRandomSolution() | Builds a random valid sequence. Used to restart SA when the temperature drops to zero. |
| SGS() | Serial Schedule Generation Scheme: decodes an activity sequence into a concrete schedule and returns the makespan. |
| isFeasibleSwap() | Checks whether swapping two positions in a sequence keeps the sequence topologically valid. |
| TS() | Tabu Search algorithm. Iteratively improves the schedule using steepest descent with a tabu list. |
| SA() | Simulated Annealing algorithm. Probabilistically accepts worse solutions to escape local optima. |

## 2.1  Global Variables & Constants

The following variables are declared globally so every function can access them without passing parameters:

| Variable | Meaning |
| --- | --- |
| n, m | Number of activities and number of resource types in the loaded instance. |
| a[RES] | Availability array. a[k] = maximum units of resource type k available per time period. |
| d[ACT] | Duration array. d[i] = how many time units activity i takes to complete. |
| r[ACT][RES] | Resource requirement matrix. r[i][k] = units of resource k needed by activity i per period. |
| nrsu[i], su[i][j] | Number of successors and the successor list for each activity i. |
| nrpr[i], pr[i][j] | Number of predecessors and the predecessor list for each activity i. |
| of[ACT] | Output finish times. of[i] = the time at which activity i finishes in the decoded schedule. |
| reach[ACT][ACT] | Reachability matrix. reach[i][j] = 1 if j is a direct or indirect successor of i. |
| allowed_time | Computation time limit entered by the user (in seconds). |
| choice[4] | The user's method selection: TS, SA, or A (for both). |
| ACT = 32 | Compile-time constant: maximum number of activities supported. |
| RES = 4 | Compile-time constant: maximum number of resource types supported. |
| MAX_T = 500 | Compile-time constant: safe upper bound on the project makespan for array sizing. |

# 3. Function-by-Function Explanation

## 3.1  input()

Purpose: reads the project data from a .rcp file and populates all global arrays. Returns 1 on success, 0 on any error.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| printf / scanf (filename) | Asks the user to type a filename, then appends .rcp to it automatically so the user does not need to type the extension. |
| fopen(filename, "r") | Opens the file for reading. If the file does not exist, fp is NULL and the function returns 0 immediately. |
| fscanf(fp, "%d %d", &n, &m) | Reads the first line: number of activities (n) and resource types (m). Checks they do not exceed the array limits ACT and RES. |
| for i1: fscanf a+i1 | Reads the second line: availability of each resource type into the array a[]. |
| for i1 < n: nrpr[i1]=0 | Initialises the predecessor count for every activity to 0 before reading the graph. |
| fscanf d+i1 | For each activity, reads its duration into d[]. |
| fscanf r[i1]+i2 | Reads the resource requirement of activity i1 for each resource type i2 into r[][]. Also checks the requirement does not exceed availability. |
| fscanf nrsu+i1 | Reads how many successors activity i1 has. |
| fscanf &i3; su[i1][i2]=--i3 | Reads each successor number (1-based in the file) and converts it to 0-based by decrementing before storing in su[][]. |
| pr[i3][nrpr[i3]++] = i1 | Simultaneously builds the predecessor list: the current activity i1 is recorded as a predecessor of activity i3. |
| if i3 <= i1 ¦¦ i3 > n | Validates that successors always have a higher index than the current activity (topological ordering) and do not exceed n. |
| fclose(fp); return 1 | Closes the file and signals success. |

## 3.2  buildReachability()

Purpose: precomputes a full reachability matrix so that during the search we can check in O(1) whether one activity must come before another.

The matrix reach[i][j] is set to 1 if activity j is a direct or indirect successor of activity i. This is the transitive closure of the precedence graph.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| for i,j: reach[i][j]=0 | Initialises every entry in the reachability matrix to 0 (no relationships known yet). |
| for i,j: reach[i][su[i][j]]=1 | Seeds the matrix with direct successor edges: if the file says i must come before su[i][j], set that cell to 1. |
| for k,i,j: Floyd-Warshall | Computes the transitive closure. The rule is: if i can reach k AND k can reach j, then i can reach j. After iterating over all intermediate nodes k, the matrix contains all reachable pairs. |

Why precompute this? During search, we check feasibility of thousands of swaps per second. Looking up reach[i][j] takes one array access (O(1)). Without this matrix, we would need to traverse the graph each time — much slower.

## 3.3  computeLST()

Purpose: computes the Latest Start Time (LST) for every activity using the Critical Path Method (CPM), ignoring resource constraints. This tells us the latest each activity can start without delaying the project.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| Forward pass: est[i]=0 | Initialises the Earliest Start Time to 0 for each activity. |
| for j < nrpr[i]: est[i] = max(eft[pr]) | EST of activity i = the maximum Earliest Finish Time among all its predecessors. An activity cannot start before all its prerequisites are done. |
| eft[i] = est[i] + d[i] | Earliest Finish Time = when it starts at the earliest + how long it takes. |
| T = eft[n-1] | The resource-free project duration is the finish time of the sink activity (last activity, index n-1, which has duration 0). |
| Backward pass: lft[i]=T | Initialises Latest Finish Time to the project end for all activities. |
| for i=n-2 downto 0 | Iterates backwards through activities. For each activity, its LFT = the minimum Latest Start Time of all its successors (i.e., it must finish before any successor needs to start). |
| lst[i] = lft[i] - d[i] | Latest Start Time = Latest Finish Time minus the activity duration. |

Float vs critical: an activity with LST = EST has zero float — it is on the critical path and must start exactly on time. An activity with LST > EST has slack and can be delayed somewhat without affecting the project end.

## 3.4  generateInitialSolution()

Purpose: creates the first activity sequence fed to TS or SA. Uses Kahn's topological sort algorithm, always choosing the most time-critical available activity next.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| computeLST(lst) | First computes LST values for all activities (see above). |
| in_deg[i] = nrpr[i] | Sets each activity's in-degree (number of unscheduled predecessors) to its total predecessor count. |
| sched[i] = 0 | Marks all activities as not yet placed in the sequence. |
| outer for pos=0..n-1 | Fills the sequence one position at a time, from first to last. |
| find ready activities | An activity is ready if it has not been placed yet (sched==0) AND all its predecessors are already placed (in_deg==0). Collects all such activities into the ready array. |
| pick min LST | Among all ready activities, selects the one with the smallest Latest Start Time. This activity is the most time-critical — delaying it risks pushing out the project end. |
| seq[pos] = best_act | Places that activity into the current position in the sequence. |
| in_deg[su[best_act][i]]-- | Reduces the in-degree of each successor: one more of their prerequisites is now placed. |

Why not random? A random topological sort ignores the critical path and often starts with a poor makespan. The LST sort puts the most constrained activities early, giving the search a much better starting point and reducing the number of iterations needed to find a good solution.

## 3.5  generateRandomSolution()

Purpose: produces a valid random activity sequence. Used exclusively to restart Simulated Annealing when the temperature has cooled to near-zero.

The logic is identical to generateInitialSolution() except the tie-breaking rule: instead of always picking the minimum-LST ready activity, it picks one at random from the ready set. This guarantees a topologically valid sequence (precedence is respected) while introducing enough randomness to explore a different region of the solution space.

## 3.6  SGS() — Serial Schedule Generation Scheme

Purpose: takes an activity sequence (a permutation of 0..n-1) and turns it into a concrete schedule by assigning a start time to each activity. Returns the makespan (finish time of the last activity).

The SGS is the core decoder. Every time we evaluate a candidate solution during TS or SA, we call SGS to find out how long the project takes.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| finish_a[ACT] = {0} | Stores the finish time of each activity once it is scheduled. Initialised to 0. |
| res_use[MAX_T][RES] = {0} | Resource usage profile. res_use[t][k] = how many units of resource k are in use at time period t. Initialised to all zeros. |
| outer for i=0..n-1 | Processes activities in the order given by the sequence. This order determines the priority — earlier in the sequence means higher priority to be scheduled. |
| act = seq[i] | Gets the actual activity number at position i in the sequence. |
| Step 1: find EST | t starts at 0 and is pushed up to the finish time of every predecessor. This is the Earliest Start Time from precedence alone. |
| Step 2: while(!feasible) | Outer loop: tries progressively later start times until a feasible one is found. |
| for tau = t..t+d[act] | Inner loop: checks every time slot within the activity's duration window [t, t+d[act]). |
| for k=0..m-1: resource check | For each resource type, checks if adding this activity's requirement to what is already booked at time tau would exceed the availability. If yes, the slot is infeasible. |
| feasible=0; then t++ | If any time slot or resource was infeasible, marks the whole attempt as failed and tries the next start time. |
| Step 3: book | Once a feasible t is found, records the finish time and adds the activity's resource consumption to every time period it runs. |
| of[i] = finish_a[i] | Copies finish times into the global of[] array so callers can inspect individual activity finish times. |
| return finish_a[n-1] | The makespan is the finish time of the sink activity (n-1), which has duration 0, so its finish time equals the latest finish time among all its predecessors. |

## 3.7  isFeasibleSwap()

Purpose: checks whether swapping two activities at positions pi and pj (pi < pj) in the sequence produces a sequence that still respects all precedence constraints.

When we swap activities at positions pi and pj, the activity that was at pj moves earlier in the sequence (to position pi), and the activity that was at pi moves later (to position pj). This can break precedence in three ways:

- The activity moving right (from pi to pj) might now be placed after one of its successors that sits between pi and pj.

- The activity moving left (from pj to pi) might now be placed before one of its predecessors that sits between pi and pj.

- The two swapped activities themselves might be in a direct/indirect predecessor-successor relationship.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| if reach[seq[pi]][seq[pj]] | Checks case 3: if the activity currently at pi is an ancestor of the activity at pj, swapping them would put the successor before its ancestor. Reject. |
| for k = pi+1..pj-1 | Checks the intermediate positions between the two swap points. |
| if reach[seq[pi]][seq[k]] | Activity at pi (moving to pj) would end up after seq[k]. But if seq[pi] must come before seq[k] (it is a predecessor), this violates precedence. Reject. |
| if reach[seq[k]][seq[pj]] | Activity at pj (moving to pi) would end up before seq[k]. But if seq[k] must come before seq[pj] (it is a predecessor), this violates precedence. Reject. |
| return 1 | If none of the above violations were detected, the swap is precedence-feasible. |

Note: resource feasibility is NOT checked here. Resource feasibility is implicitly handled by SGS, which always finds the earliest resource-feasible start time for each activity in the given order. So any precedence-feasible sequence can always be decoded into a valid (though perhaps not optimal) schedule.

## 3.8  TS() — Tabu Search

Purpose: improves the current best schedule iteratively using steepest descent, while preventing revisiting recently explored swaps via a tabu list. Runs until the time limit expires.

Key data structures inside TS:

- cur_seq[]: the sequence currently being explored (can be worse than the best).

- best_seq[]: the best sequence found so far across all iterations.

- tabu_exp[a][b]: the iteration number at which the tabu on swapping activity pair (a,b) expires. 0 means not tabu.

- freq[a][b]: how many times activity pair (a,b) has been swapped in total. Used in the frequency penalty.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| Initialise arrays to 0 | Sets all tabu expiry times and swap frequencies to zero before the search begins. |
| generateInitialSolution | Seeds cur_seq with the LST-ordered smart sequence and immediately evaluates it with SGS to get the initial makespan. |
| sq_n = sqrt(n) | Precomputes the floor of sqrt(n) once, used repeatedly to calculate dynamic tabu tenures. |
| outer while(1) | Main search loop. Runs indefinitely until elapsed time exceeds the limit. |
| elapsed check | At the start of each iteration, checks how much wall-clock time has passed. Stops if the limit is reached. |
| iter++ | Increments the iteration counter. Used to set and compare tabu expiry times. |
| for i,j: all swap pairs | Steepest descent: enumerates every possible pair of positions (i < j) in the current sequence. |
| isFeasibleSwap check | Skips the pair immediately if swapping would violate precedence. |
| canonical pair fa,fb | Ensures the activity pair is always stored with the smaller activity index first, so freq[a][b] and tabu_exp[a][b] are accessed consistently regardless of the order the pair was identified. |
| temp swap + SGS | Temporarily performs the swap, evaluates the resulting makespan with SGS, then undoes the swap to leave cur_seq unchanged. |
| raw_delta | The raw change in makespan: positive means the swap makes things worse, negative means better. |
| adj_delta = raw + freq/3 | Adjusted delta adds a frequency penalty. Swaps that have been used many times are artificially made to look worse, discouraging the search from cycling. |
| is_tabu check | Checks whether this swap is currently on the tabu list (its expiry iteration is still in the future). |
| aspiration | Override: even if the swap is tabu, accept it if it produces a new global best. This prevents the tabu list from blocking genuinely good moves. |
| if (!is_tabu ¦¦ aspiration) && adj_delta < best_adj | Selects the best non-tabu move (or tabu move meeting aspiration) across all candidates. |
| commit best move | Performs the selected swap permanently on cur_seq, then calls SGS to update the makespan and refresh of[]. |
| freq[fa][fb] += 1 | Records that this activity pair has been swapped one more time. |
| tabu_exp = iter + sq_n + rand()%(sq_n+1) | Sets the tabu expiry to a random number of iterations in the range [sqrt(n), 2*sqrt(n)] from now. Dynamic tenure avoids predictable cycling. |
| update best if improved | If the committed move produced a new best makespan, copies cur_seq into best_seq. |
| final SGS(best_seq) | At the end, re-runs SGS on best_seq to ensure of[] reflects the global best solution. |

## 3.9  SA() — Simulated Annealing

Purpose: explores the solution space probabilistically, occasionally accepting worse solutions to escape local optima. Temperature controls how adventurous the search is — high temperature means more exploration, low temperature means more exploitation.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| T = 15.0 | Initial temperature. Set to 15 based on the typical scale of makespan deltas in RCPSP instances of this size. |
| generateInitialSolution | Same smart LST-based starting point as TS. |
| outer while(1) | Runs until the time limit is reached. |
| inner for it=0..n-1 | Runs n iterations (one per activity in the instance) at the current temperature before cooling. This is one temperature epoch. |
| random swap selection | Picks two random positions a1 < a2 and checks feasibility. Tries up to n*n times to find a feasible swap. If none found, skips this iteration. |
| swap + SGS + delta | Performs the swap, evaluates the new makespan, computes the change delta = new - current. |
| if delta <= 0: accept | If the swap improves or matches the current makespan, always accept it and update the best if applicable. |
| else: Boltzmann probability | If the swap is worse (delta > 0), accept it with probability exp(-delta/T). At high T, even large worsening moves are often accepted. As T drops, only small worsening moves have a chance. |
| else: undo swap | If the probabilistic acceptance fails, reverses the swap to restore cur_seq. |
| T *= 0.8 | Geometric cooling: reduces temperature by 20% after every epoch of n iterations. |
| if T < 0.001: restart | When the temperature is effectively zero (no exploration possible), resets T to 15 and generates a fresh random topological sort. This allows SA to explore a completely different region of the solution space. |
| final SGS(best_seq) | At the end, re-runs SGS on best_seq to ensure of[] reflects the global best solution. |

## 3.10  main()

Purpose: the program entry point. Coordinates user input, data loading, and algorithm dispatch.

| Code / Line | Plain-Language Explanation |
| --- | --- |
| input() | Asks for filename, reads and validates the project data. Returns 0 on error. |
| buildReachability() | Precomputes the reach[][] matrix immediately after loading — done once, used throughout. |
| srand(time(NULL)) | Seeds the random number generator with the current time so each run produces different random choices. |
| scanf allowed_time | Asks the user how many seconds the algorithm is allowed to run. |
| scanf choice | Asks whether to run TS, SA, or A (both). Stored as a character string. |
| x = 0; if choice==65: x=2 | 65 is the ASCII code for 'A'. Setting x=2 makes the loop run twice (once for TS, once for SA). |
| for i1=0..x | Outer loop iterates once for single-method runs and twice for 'A' mode. |
| choice==84: TS(allowed_time) | 84 is ASCII 'T'. Runs the full Tabu Search for the allowed time. |
| choice==83: SA(allowed_time) | 83 is ASCII 'S'. Runs the full Simulated Annealing for the allowed time. |
| choice==65: TS/SA half time | For 'A' mode: first iteration runs TS for half the time, second runs SA for the remaining half. |
| getch() | Waits for a keypress before closing the window, so the user can read the output. |
| _CrtDumpMemoryLeaks() | Visual Studio debug function that reports any memory not freed. Confirms no memory leaks. |

# 4. Key Model Choices and Their Effect

## 4.1  Activity List Representation

The solution is represented as a permutation of activity indices — an ordered list telling the SGS which activity to schedule next. This is the standard representation for RCPSP metaheuristics because:

- Every permutation that respects topological order decodes to a valid (resource and precedence feasible) schedule via SGS.

- It separates the search space (the sequence) from the evaluation (the schedule). The search only needs to explore sequences; SGS handles all feasibility concerns.

- Moves (swaps) in sequence space are simple and cheap to generate.

## 4.2  Serial vs Parallel SGS

This code uses the Serial SGS. The alternative is the Parallel SGS, which works by advancing a time counter and at each time point schedules all activities that are both eligible and resource-feasible.

- Serial SGS: schedules activities one by one in sequence order, each at its earliest feasible time. Better for metaheuristics because small changes in the sequence produce small changes in the schedule (smooth search landscape).

- Parallel SGS: can produce more compact schedules on some instances but is harder to combine with sequence-based neighbourhoods.

## 4.3  Swap Neighbourhood

The neighbourhood of a solution consists of all sequences reachable by swapping two positions. We only consider precedence-feasible swaps (checked by isFeasibleSwap). Swaps are preferred over insert moves because:

- Simpler to implement and verify.

- Symmetric: swapping (i, j) and then swapping back returns to the original solution, which makes tabu logic cleaner.

- Well-studied: swap neighbourhoods are the standard in RCPSP literature.

## 4.4  Tabu List Design

The tabu list is move-based: it tracks pairs of activities (not positions). When activities a and b are swapped, the pair (a, b) is forbidden for the next T iterations, where T is drawn from [sqrt(n), 2*sqrt(n)].

- Move-based vs solution-based: storing the activity pair is much lighter than hashing the full sequence, and avoids collisions.

- Activity pairs vs position pairs: if we banned positions i and j, the same two activities could be swapped again at different positions in a later iteration. Banning the activity pair is a stricter and more meaningful restriction.

- Dynamic tenure: using a random tenure in [sqrt(n), 2*sqrt(n)] prevents the search from adapting to a fixed tenure and cycling with a different period.

## 4.5  Frequency Penalty

Formula:  adjusted_delta = raw_delta + freq[a][b] / 3.0

The frequency penalty is a long-term memory mechanism. Raw delta measures the quality of a move (negative = improvement). The penalty adds a positive term proportional to how many times this pair has been swapped before. This makes frequently-used moves look worse in steepest descent, pushing the search toward less-explored swaps. The divisor 3 controls the strength of the penalty — larger values make the penalty weaker.

- Effect with freq=0: move evaluated purely on merit.

- Effect with freq=3: move penalised by +1, so a move that improves by 1 now looks neutral.

- Effect with freq=9: move penalised by +3, so it would need to improve by more than 3 to be chosen.

## 4.6  Aspiration Criterion

A tabu move is accepted anyway if it produces a new global best makespan. Without this rule, the tabu list could permanently block paths to the optimal solution. The aspiration criterion is a safety valve: if a forbidden move leads somewhere better than anything seen before, the restriction is lifted.

## 4.7  LST-Based Initial Solution

Starting from a smart solution rather than a random one reduces the number of iterations needed to reach a good makespan. The LST ordering approximates the critical path ordering: activities with the least scheduling flexibility come first. In practice this often produces a makespan within a few percent of optimal before any search begins.

## 4.8  SA Temperature and Cooling

- T0 = 15: chosen to match the scale of typical makespan improvements in j30-class instances (a single swap typically changes makespan by 0-5 time units). At T=15, a worsening move of +5 is accepted with probability exp(-5/15) ≈ 71%.

- alpha = 0.8: aggressive cooling. Temperature halves roughly every 3 epochs. This means SA transitions quickly from exploration to exploitation — appropriate when restarts are used.

- n iterations per epoch: ties the epoch length to the problem size. Larger instances get more evaluations per temperature level.

- Restart at T < 0.001: rather than terminating, SA resets to T=15 with a fresh random sequence. This transforms SA into an iterated multi-start procedure, combining the local exploitation of SA with the global diversification of random restarts.

## 4.9  Steepest Descent in TS vs Random in SA

TS evaluates every feasible swap in the neighbourhood and picks the best one (steepest descent). SA picks one random feasible swap per step. This is intentional:

- TS needs steepest descent to make the tabu mechanism meaningful. Without it, we would just pick any non-tabu move, which is too arbitrary.

- SA relies on randomness for its theoretical properties (ergodicity, convergence). Steepest descent in SA would bias it toward the nearest local optimum and remove the ability to escape.

# 5. Pseudocode of Key Functions

## 5.1  SGS — Serial Schedule Generation Scheme

function SGS(sequence):

finish_time[0..n-1] = 0

resource_profile[0..MAX_T][0..m-1] = 0

for each activity act in sequence order:

// Step 1: precedence constraint

t = max(finish_time[p] for all predecessors p)

// Step 2: resource constraint

if activity has positive duration:

found_slot = false

while not found_slot:

found_slot = true

for each time unit tau in [t, t+d[act]):

for each resource k:

if resource_profile[tau][k]

+ r[act][k] > a[k]:

found_slot = false

if not found_slot:

t = t + 1   // try next start time

// Step 3: book the activity

finish_time[act] = t + d[act]

for tau in [t, t+d[act]):

resource_profile[tau][k] += r[act][k]

makespan = finish_time[last activity]

return makespan

## 5.2  Tabu Search

function TS(time_limit):

tabu_expiry[all pairs] = 0

frequency[all pairs]  = 0

current_seq  = LST_based_initial_solution()

best_seq     = current_seq

best_makespan = SGS(current_seq)

current_makespan = best_makespan

iteration = 0

while elapsed_time < time_limit:

iteration++

best_delta = infinity

best_move  = none

// Steepest descent: evaluate all feasible swaps

for every pair of positions (i, j) with i < j:

if not isFeasibleSwap(i, j):  skip

(a, b) = canonical activity pair at positions (i, j)

temporarily swap positions i and j

new_makespan = SGS(current_seq)

undo swap

raw_delta  = new_makespan - current_makespan

adj_delta  = raw_delta + frequency[a][b] / 3

is_tabu    = (tabu_expiry[a][b] > iteration)

aspiration = (new_makespan < best_makespan)

if (not is_tabu OR aspiration):

if adj_delta < best_delta:

best_delta = adj_delta

best_move  = (i, j, new_makespan)

if best_move found:

perform best_move on current_seq

current_makespan = SGS(current_seq)

frequency[a][b] += 1

tenure = random integer in [sqrt(n), 2*sqrt(n)]

tabu_expiry[a][b] = iteration + tenure

if current_makespan < best_makespan:

best_makespan = current_makespan

best_seq = current_seq

return best_seq, best_makespan

## 5.3  Simulated Annealing

function SA(time_limit):

T            = 15.0   // initial temperature

alpha        = 0.8    // cooling rate

epoch_length = n      // iterations per temperature level

current_seq  = LST_based_initial_solution()

best_seq     = current_seq

best_makespan = SGS(current_seq)

current_makespan = best_makespan

while elapsed_time < time_limit:

// One temperature epoch

for step = 1 to epoch_length:

if elapsed_time >= time_limit:  break

// Pick a random feasible swap

pick two random positions (i, j) with i < j

if not isFeasibleSwap(i, j):  retry (up to n^2 tries)

swap positions i and j in current_seq

new_makespan = SGS(current_seq)

delta = new_makespan - current_makespan

if delta <= 0:

// Accept improvement

current_makespan = new_makespan

if current_makespan < best_makespan:

best_makespan = current_makespan

best_seq = current_seq

else:

// Accept worse solution with probability

p = exp(-delta / T)

if random() < p:

current_makespan = new_makespan

else:

undo swap  // reject the move

// Cool down

T = T * alpha

// Restart if temperature effectively zero

if T < 0.001:

T = 15.0

current_seq = random_topological_sort()

current_makespan = SGS(current_seq)

return best_seq, best_makespan

# 6. Reading the Output

After running, the program prints one block per algorithm executed:

--- Tabu Search Results ---

Best sequence : 1 32 3 5 7 2 4 ... 31

Best makespan : 55

- Best sequence: the activity indices in the order they should be fed to the SGS to reproduce the best schedule found. Indices are 1-based (matching the input file numbering). The source activity (index 1) is always first and the sink (index n) is always last.

- Best makespan: the project duration in time units. Lower is better. This is the finish time of the sink activity under the best decoded schedule.

To verify: feed the printed sequence back into SGS manually. The finish time of the last activity should exactly equal the printed makespan.

# 7. Quick Reference

## Algorithm Parameters

| Parameter | Value | Rationale |
| --- | --- | --- |
| Tabu tenure | Random in [sqrt(n), 2*sqrt(n)] | Dynamic range prevents predictable cycling patterns. |
| Frequency divisor | 3 | Controls penalty strength; larger = weaker penalty. |
| SA initial temperature | 15 | Calibrated to RCPSP makespan delta scale (~0-5 units). |
| SA cooling rate | 0.8 | Aggressive; combined with restarts for wide coverage. |
| SA epoch length | n (num. activities) | Scales exploration per temperature to problem size. |
| SA restart threshold | T < 0.001 | Temperature effectively zero; restart with new solution. |

## Function Call Map

main()

|-- input()

|-- buildReachability()

|-- TS(time_limit)

|     |-- generateInitialSolution()

|     |     |-- computeLST()

|     |-- SGS()          [many times]

|     |-- isFeasibleSwap()

|

|-- SA(time_limit)

|-- generateInitialSolution()

|     |-- computeLST()

|-- generateRandomSolution()

|-- SGS()          [many times]

|-- isFeasibleSwap()